## Sakchyam Log frame_30 Sep 019
Sakchyam Access to Finance Programme Logical Framework (Revised Indicators as per the Budget Allocated to the Access to Finance Programme, and Over Achieved Indicators)
PROJECT NAME | ACCESS TO FINANCE FOR POOR (AFP) PROGRAMME | [8 empty] | Remarks | Revisions to note
Based on Results from Implementation Phase - December 2014 to December 2019
IMPACT | Impact Indicator 1 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
28528337.808
Sustainable improvements in the livelihoods of poor people | Number of sustainable new jobs created | Planned | 0 | 5000 | 15000 | 30000 | 60000 | 88000
|  | Planned (as per AFP contract amount) | 0 | 3135.5932 | 9406.7797 | 18813.5593 | 37627.1186 | 55186.4407
|  | Achieved |  | 1356.4286 | 9907
Source: Reports from partners providing loan funds disbursed to borrowers.
Increase in income of NPR 40,000 is considered as equivalent to one new job created in the DFID-AFP business case. Income increase is derived from loan disbursed to beneficiaries by the partner BFIs considering that income increases by £0.3 per £1 loan borrowed by the beneficiaries (based on Sakchyam M&E Baseline Survey 2015 findings) and further imputed for the purpose of new jobs created.
|  |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-June,'016) | Milestone Year 3 | Milestone Year 4 | Target Year 5
| Percentage of jobs created for women | Planned |  | 30% | 40% | 50% | 50% | 50%
|  | Planned (as per AFP contract amount) |  | 30% | 40% | 50% | 50% | 50%
|  | Achieved |  | 24% | 49%
Source: Based on partners' reports on loan funds made available for women borrowers.
Increase in income of NPR 40,000 is considered as equivalent to one new job created in the DFID-AFP business case. Income increase is derived from loan disbursed to women beneficiaries by the partner BFIs considering that income increases by £0.3 per £1 loan borrowed by the beneficiaries (based on Sakchyam M&E Baseline Survey 2015 findings) and further imputed the purpose of new jobs created.
Comment
Sustainable improvements in the livelihoods of poor people | Net increase in income at the borrower (beneficiary) level as a result of Sakchyam Programme Interventions | Planned | 0 | 270000 | 2700000 | 6750000 | 10800000 | 14580000
|  | Planned (as per AFP contract Budget) | 0 | 187627.1186 | 1876271.1864 | 4690677.9661 | 14310192.24 | £ 37,332,000 * | £ 44,135,182 *
|  | Achieved |  | 361714.2857 | 3872677 | 13463634 | 30522727.1809 | 39402773 | 74379707.2088 | `
Source: Reports from partners providing loan funds disbursed to borrowers.
Income increase is derived from loan disbursed to beneficiaries by the partner BFIs considering that income increases by £0.24 per £1 loan borrowed by the beneficiaries (based on Sakchyam Mid-term Evaluation Survey 2019 findings).By investing the principal borrowed in agriculture and non-agricultural economic activities/MSMEs, beneficiaries realize a 24% net increase in income. Loan fund disbursed by partner BFIs to target group is one of the key indicators for monitoring. Increased income at beneficiaries level is directly dependent on the loan disbursed to the beneficiaries for the productive investment. Sakchyam encourages partners to disburse more loans to productive sectors both in terms of number of beneficiaries, volume of loan including encouragment and support to design and implement appropriate loan product (s), promote financial literacy and provide enterprise related trainings to help increase demand for loan and investment. Saving generates some interest (different rate) as well as funds for investment that attribute to increase in income. Furthermore, the actual attribution measurement of income increased will be measured at the end-line surveys.
Comments
| Impact Indicator 2 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| 50% of the net increase in income is for women beneficiaries as a result of Sakchyam Programme Interventions | Planned | 0 | 135000 | 1350000 | 3375000 | 5400000 | 7290000
|  | Planned (as per AFP contract Budget) | 0 | 93813.5593 | 938135.5932 | 2345338.9831 | 7155096.12 | £ 20,841,278 * | £ 22,067,591 *
|  | Achieved |  | 188091.4286 | £ 2,431,552 | 9135701 | 20914230.3979 | 27503181 | 46779114.6108
Source: Reports from partners disbursing loan funds to borrowers.
Income increase for women beneficiareis is derived from loan disbursed to women beneficiaries by the partner BFIs considering that income increases by £0.24 per £1 loan borrowed by the women beneficiaries (based on Sakchyam Mid-term Evaluation Survey 2019 findings).By investing the principal borrowed in agriculture and non-agricultural economic activities/MSMEs, beneficiaries realize a 24% net increase in income. Loan funds disbursed by partner BFIs targeted to women beneficiaries is one of the key monitoring indicators. Increased income at women beneficiaries' level depends on the loans disbursed to women beneficiaries for productive investment in enterprises, agriculture and livestock activities. Sakchyam encourages and supports partner BFIs to disburse more loans in productive sectors, including for women beneficiaries: i) increased loan volumes and number of women beneficiaries, ii) design and implement appropriate loan product(s) targeted to women, iii) promoting financial literacy and iv) providing enterprise related trainings. These will help increase demand from women beneficiaries for loan and investment. Similarly, savings by women beneficiaries generate interest income and additional funds for investment that lead to increase in income. Furthermore, the actual attribution measurement of income increased will be measured at the end-line survey.
|  | Comments | Loan funds disbursed by partner BFIs to targeted beneficiaries is one of the key monitoring indicators. Increased income at beneficiaries' level directly depends on the loans disbursed to the beneficiaries for productive investment. AFP/Sakchyam needs to encourage and support partners to disburse more loans in productive sectors, including: i) increased loan volumes and number of beneficiaries, ii) design and implementation of appropriate loan product(s), iii) promoting financial literacy and iv) providing enterprise related trainings. These will help increase demand for loan and investment. Savings generate interest income additional funds for investment that lead to increase income, But actual attribution measurement basis will be undertaken in mid-line and end-line surveys.
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) | Assumptions
Greater access to a range of financial services for enterprises and households | Leveraged funds that further increase investments in productive sectors (i.e. leverage achieved) (A5.1) | Planned | £0 | 1000000 | 10000000 | 25000000 | 40000000 | 54000000 |  | Political instability does not increase.
|  | Planned (as per AFP contract Budget) | £0 | 694915.2542 | 6949152.5424 | 17372881.3559 | 53000712 | £ 183,000,000 * | £ 220,000,000 *
|  | Achieved |  | 854140 | £ 17,904,015 | 58111457 | 133635666 | 194636814.3889 | 194636814.3889 | Limited exogenous shocks to the economy. | To be imputed based on Dec 2019
Source: Partners report on total expenditures and loans disbursed.
Leveraged fund = loans disbursed + amount of funds invested by the private sector in the productive sector for the development of new financial product/service + premium paid for insurance by the beneficiaries (average 5% of insurance amount) + down payment made by beneficiaries as an equity investment (average 25 % of loan disbursed by BFIs) in productive activities such as agriculture, livestock and MSMEs + savings at non-lending BLB touch points.
Comments
|  | Comments | Leveraged amount is calculated based on partner's investment in the project and loan fund disbursed to the beneficiaries. However, savings by the beneficiaries in the partner BFIs are not considered as leveraged fund because one of the fund source for loan fund that disbursed by the partner to the beneficiaries comes from the deposited amount.
| Outcome Indicator 2 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) | Macroeconomic stability persists.
| Number of people gaining new access to a range of financial products and services (A5.2) | Planned | 0 | 7000 | 73000 | 140000 | 300000 | 400000 |  | Limited shocks due to climatic and other natural disasters.
|  | Planned (as per AFP contract Budget) | 0 | 4864.4068 | 50728.8136 | 97288.1356 | 302099 | 850000 | 1590000 | No political or environmental constraints to women from participating in the program or having access to financial services.
|  | Achieved |  | 7804 | 92829 | 208360 | 404762 | 1088192 | 1830788
Source: Partner's report on Outreach.
Range of financial products and services (i.e., savings, loans, remittances, G2P payments and insurance) accessed by people/housholds in programme districts through partner BFIs.
Comments
| Outcome Indicator 3 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| Number of MSMEs with improved financial access through financial institutions (A5.3) | Planned | 0 | 600 | 2000 | 4000 | 6000 | 8000
|  | Planned (as per AFP contract Budget) | 0 | 416.9492 | 1389.8305 | 2779.661 | 22897 | 71,000 * | 80,000 *
|  | Achieved |  | 674 | 10507 | 18317 | 42502 | 75766 | 86430
Source: Partners report on MSMEs reached.
Range of financial products and services (i.e., savings, loans, remittances, and insurance) accessed by MSMEs in programme districts through partner BFIs.
Comments
| Outcome Indicator 4 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Sep.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| Percentage of women gaining new access to a range of financial products and services (A5.4) | Planned |  | 10% | 30% | 40% | 50% | 50%
|  | Planned (as per AFP contract Budget) | 0 | 10% | 30% | 40% | 50% | 50% | 50%
|  | Achieved |  | 86% | 59% | 64% | 63.67% | 55% | 56%
Source: Partners report on outreach to women.
Range of financial products and services (i.e., savings, loans, remittances, G2P payment, and insurance) accessed by women as a percentage of total number of people gaining access in programme districts through partner BFIs. The higher achievements are attributable to AFP/Sakchyam's engagement with MFIs that largely serve women.
|  | Comments | Percent of women gaining new access reduced in second year. Sakchyam need to emphasize on women targeted interventions to maintain this indicator such as promote women targeted products, increase outreach through MFIs
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
£ 18.5 Million + £ 2 Million
INPUTS (HR) | DFID (FTEs)
1 Adviser, 2 Programme Manager, 1 Programme Officer
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) | Assumption | Components to recheck on the numbers and possible additions. Additions to be reported in single document. (C1- Raju) - one in march deliverable
Banks and other financial institutions are able to provide more and better services to enterprises | Number of new financial products launched for small and medium enterprises (SMEs) (A1.3c) | Planned | 0 | 2 | 4 | 6 | 10 | 12 |  | GDP growth continues at current rate or higher
|  | Planned (as per AFP contract Budget) | 0 | 2 | 4 | 6 | 8 | 10 | 11
|  | Achieved |  | 2 | 5 | 6 | 8 | 10 | 10
|  | Source: Partners reports on new products launched or deliverable reports. | [7 empty] | Continued improvement in the business enabling environment, particularly the regulatory environment
New financial products launched include: i) Invoice discounting (BOK); ii) Warehouse receipts financing (Global IME); iii) Micro-mortgage loan to low income households and low value home loan product (Laxmi Bank); (iv) Sakchyam Udhyami Karja (Laxmi Bank); (v) Dairy financing products for milk farmers (NMB Bank); (vi) Saral Biu-Bijan Karja (Kanchan Dev. Bank); (vii).Sajilo Khetipati Karja (BoK); (viii) MBL Sanakisan Karja (Machhapuchhre Bank); (ix) Prabhu Bhandaran Karja (Prabhu Bank); and (x) Nabil Sajilo Karja (Nabil Bank).
Comments by Output Lead
| Output Indicator 1.2 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) |  | Components to recheck on the numbers and possible additions (C1-Samin) - in march deliverable
| Number of branches of banks that increase their MSME portfolio by 20% or more (A1.3b) | Planned | 0 | 1 | 2 | 5 | 6 | 7
|  | Planned (as per AFP contract Budget) | 0 | 1 | 2 | 3 | 4 | 6 | 7
|  | Achieved |  | 1 | 2 | 3 | 4 | 6 | 6
Source: Partners reports or deliverable reports
6 branches of partner banks have increased their MSME portfolio by 20% or more: (i) BoK - Belauri branch; (ii) Mega bank - Sanfebagar branch; (iii) Sanima bank - Nuwakot branch; (iv) Mega bank - Khalanga branch; (v) NIBL - Dipayal, Doti; and (vi) Sanima Bank - Manma, Kalikot.
Comments by Output Lead
| Output Indicator 1.3 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) |  | Programme/TL team to recheck on possible additions
| Number of capacity building initiatives supported for public sector stakeholders (A1.1a) | Planned | 0 | 3 | 5 | 6 | 9 | 9
|  | Planned (as per AFP contract Budget) | 0 | 3 | 5 | 6 | 7 | 8 | 9
|  | Achieved |  | 4 | 6 | 6 | 6 | 8 | 10
Source: Legal/Regulatory Annual Progress Review Reports; Regulatory Body Circulars/Directives
Regulatory body actions resulting through capacity building initiatives from Sakchyam: (i) NRB mandating the membership by MFIs in the Credit Information System; (ii) NRB Relaxation on requirements to open Branchless Banking touch points in earthquake affected districts; (iii) NRB Relaxation on know-your-customer (KYC) requirements for the purpose of new account openings; (iv) Increase accorded by NRB in loan limits for micro-enterprises; (v) Increase accorded by NRB on loan ceiling for the first time individual microfinance borrower; (vi) Allowed branchless banking in municipalities by NRB, to deliver limited banking services in the new federal system; (vii) Amendment of NRB PSD directives#5: transaction limits, (viii) Payment and settlement Act 2019, (ix) Establishment of commercial bank branches to facilitate G2P payments through bank accounts and (x) Supporting NRB PSD Directive #8 on Online Reporting by PSP and PSO
Comments by Output Lead
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| Percent increase / increase in absolute value in guaranteed MSME loans issued to borrowers. (A1.6d) | Planned | 0 | 10% | 20% | 40% | 60% | 100%
|  | Planned (as per AFP contract amount) | 0 | 10% | 20% | 40% | 147% | NPR 2,000,000,000 * | NPR 2,200,000,000 *
|  | Achieved |  | 32.42% | 132% | 1890% | 1890% ( 1,830,000,000) | NPR 2,026,471,378 | NPR 2,026,471,378
|  | Source: Output 1 deliverable report | [7 empty] | RISK RATING
Partner banks have shown increase in the amount of guaranteed loans made available to targeted borrowers.
Comments by Output Lead
| Output Indicator 1.5 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| RTGS and CSD System adopted by Nepal Rastra Bank (Central Bank of Nepal) (A1.5b) | Planned (as per AFP contract Budget) | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Achieved | [5 empty] | 1 | 1
|  | Source: Output 1 deliverable report | [7 empty] | RISK RATING
Implement RTGS and CSD systems at NRB that will provide: i) reduction in systemic risk through ensuring real-time settlement and increased systemic efficiency for customers and banks; ii) to meet international best practices. Status :RTGS system installed and operations started.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) | Assumptions | C2 to recheck on the % increase. Note: Yr 6 target already achieved.
Strengthened capacity of formal and semiformal financial institutions to provide services in selected districts | Increased capacity of Financial Institutions (FIs) (A2.5) | Planned | 0 | 10% | 25 % | 50 % | 75 % | 100 % |  | Government remains supportive in increasing access to financial services for poor people
|  | Planned (as per AFP contract Budget) | 0 | 10% | 25% | 50% | 75% | 100% | 110%
|  | Achieved |  | 23.88% | 50.4% | 51.4% | 60.5% | 217% | 217%
Source: Report on capacity improvement of selected partner institution
Year 1 - Results in capacity improvement by partner based on pre-set capacity improvement indicators. Year 2 - Assessment of increase in capacity of VLBS. Year 3 - Assessment of increase in capacity : VLBS (51.4 % increased capacity against 50% target), and Kisan Cooperatives ( 52.2% increased capacityagainst 25% target). Year 4 - Partner FIs of Sakchyam i.e. VLBS microfinance institution and Kisan Cooperative have been considered as sample to assess the Indicator-Increased Capacity of FIs. Interim reporting under Milestone - year 4 is 60.50% which is based on the provisional figures. As of date, tenure of partnership between Sakchyam and FIs is less than five years; The indicator is expected to be achieved within five years of partnership. Year 5 - VLBS microfinance institution considered as sample to assess the increased capacity.
Comments by Output Lead
| Output Indicator 2.2 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) | Continued expansion of communications infrastructure | Components to recheck on the numbers and possible additions
| Partner FIs adopting mobile-enabled and online core loan administration system. (A2.7a) (A2.10a) | Planned | 0 | 1 | [5 empty] | Appropriate regulatory approach taken to agent and mobile banking
|  | Planned (as per AFP contract Budget) | 0 | 1 | 3 | 4 | 8 | 9 | 10
|  | Achieved |  | 1 | 4 | 7 | 7 | 11 | 12
Source: Output 2 deliverable report
FIs adopting mobile enabled core loan administration system include:(i) Kisan Microfinance, (ii) Kisan Cooperative, (iii) Chhimek Laghubitta, (iv) Sahara Cooperative, (v) Nirdhan Uththan Laghubitta, (vi) UNYC Nepal, (vii) NMB - MF, (viii) Sanakisan Bikas Laghubitta Bitiya Sanstha Ltd., (ix) Mahila Samudayik (NWCSC), (x) NERUDE, (xi) Mahila Shayatra, and (xii) Janauththan.
Comments by Output Lead
| Output Indicator 2.3 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| Number of financial products and services piloted and implemented in selected districts of which [number designed] to be appropriate for women and [number developed/adapted] to promote climate change resilience (A1.8b) | Planned | 0 | 1 (1) [0]
|  | Planned (as per AFP contract Budget) | 0 | 1 (1) [0] | 3 (2) [1] | 4 (3) [1] | 6 (4) [2] | 7 (4) [3] | 8 (4) [4] |  | Components to recheck on the numbers and possible additions. To be discussed further on way forward.
|  | Achieved |  | 1 (1) [0] | 3 (2) [1] | 4 (3) [1] | 6 (4)[2] | 7(4) [3] | 7(4) [3]
Source: Output 2 deliverable report
New financial products developed and adopted include: (i) BoK new loan product " Mahila Udyam Karja" specifically targeted for women developed and launched with a partner financial institution; (ii) Mega Bank women-specific micro loan product - group loan; (iii ) Shikhar Insurance-weather-based index insurance product on apple (iv) Janata Bank- Janata Women Entrepreneur Loan, (v) Sanima Bank - Tailored women specific financial products developed/re-engineered, (vi) Jana Uththan - Energy loan product; and (vii) Shikhar Insurance - weather based index insurance product on paddy.
Comments by Output Lead
| Output Indicator 2.4 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) |  | Components to recheck on the numbers and possible additions. To further discuss where to keep A.2.8 products. (C2/C3 - Jagadish)
| Number of financial products created linking with commercial banks and other institutions in selected districts(A2.9) and A2.8 | Planned | 0 | 1
|  | Planned (as per AFP contract amount) | 0 | 1 | 3 | 5 | 8 | 9 | 10
|  | Achieved |  | 1 | 4 | 7 | 9 | 10 | 10
Source: Output 2 deliverable report
Linkage established between commercial banks and other institutions to introduce financial prodcts and services: (i) Dairy Cooperatives and NMB Bank to introduce wholesale loan; (ii) BOK and UMCL to introduce wholesale loan; (iii) UNYC-NMB partnership for Solar Loan product; (iv) NIA and NMBA to distribute microinsurance to low-income households; (v) RBB and 14 various types of cooperatives; (vi) Machhapuchhre Bank and 3 Cooperative Societies promoted by Heifer Project International; (vii) BOK and Kisan Bahuudeshya Sahakari Sanstha wholesale loan product; (viii) Mega Bank and Ramaroshan wholesale loan product; (ix) VLBS and Cooperatives, and (x) Janauttha and AEPC - alternative energy loan refinancing.
Comments by Output Lead
| Output Indicator 2.5 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Sep.,'016) | Milestone Year 3 (Dec.'014-Dec.,'016) | Milestone Year 4 (Dec.'014-Aug.'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| Number of customers in selected districts using mobile-based financial services(A2.10) | Planned | 0 | 4000 |  |  | 30000 | 50000
|  | Planned (as per AFP contract amount) | 0 | 2508.4746 | 5017 | 9407 | 126765 | 770,000 * | 1,395,000 *
|  | Achieved |  | 5216 | 28019 | 90148 | 269723 | 801137 | 1152098
Source : Partners' reports; 2.10 Deliverable Report
Includes financial products and services that have been provided to clients through alternate delivery channels (such as mobile phones;BLBs, IVR, PoS devices, tablets, and digital wallet).
Comments by Output Lead
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) | Assumptions | Components to recheck on the numbers and possible additions(C3- Omkar)
Financial capability of enterprises and households is improved in selected districts | Number of financial literacy initiatives supported through financial institutions (A3.4) | Planned | 0 | 1 | 3 | 5 | 7 | 10 |  | Government completes the design of an appropriate Financial Literacy Strategy
|  | Planned (as per AFP contract amount) | 0 | 1 | 3 | 5 | 6 | 7 | 8
|  | Achieved |  | 4 | 5 | 5 | 7 | 8 | 8
Source: Output 3 deliverable report
Financial literacy initiatives introduced with different partner institutions include: (i) IVR based Financial Literacy initiated, (ii) a year-round 12-module financial education curriculum used in PGT and center meetings, (iii) Financial literacy using TAB and mini-projector, (iv) FM Radio broadcasts, (v) Financial literacy through cable TV, (vi) Street drama, (vii) Financial Literacy Buzz (mobile vehicle), and (viii) Financial Literacy on Branchless Banking
Comments by Output Lead
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| Number of households (No. of people trained - considered as household reached) reached with new financial education products and services (A3.4a) | Planned | 0 | 20000 | 65000 | 120000 | 240000 | 300000
|  | Planned (as per AFP contract amount) | 0 | 12542.3729 | 40762.7119 | 75254.2373 | 150508.4746 | 335,000 * | 395,000 *
|  | Achieved |  | 7571 | 80840 | 120759 | 216142 | 354507 | 402342
|  | Source: Partners' reports | [7 empty] | RISK RATING
Partner BFIs have been providing financial literacy to beneficiaries through PGT, group meetings, IVR, tablets (TAB) and mobile vehicle. Financial literacy being imparted with partners to households through mass media (i.e., FM Radio, TV, street drama) are not included.
Comments by Output Lead
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020) | Assumptions
Financial Sector Deepening Facility designed, agreed and established | Design of programme from years 4-5 onwards completed and approved | Planned | 0 |  |  |  |  | Approved |  | Agreement between Government and DFID (and other donors if appropriate) on modalities for the programme.
|  | Achieved | [5 empty] | Submitted to DFID
Source: Deliverable report
Comments
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | Milestone Year 1 (Dec'014-Aug'015) | Milestone Year 2 (Dec.'014-Aug.,'016) | Milestone Year 3 (Dec.'014-Aug.,'017) | Milestone Year 4 (Dec.'014-Aug.,'018) | Target Year 5 (Dec.'014-Aug.'019) | Target Year 6 (Dec.'014-Aug.'020)
| Financial Sector Deepening Facility established and operational | Planned | [6 empty] | Established and Operational
Achieved
|  | Source: Deliverable report | [7 empty] | RISK RATING
Comments
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
5 Million
INPUTS (HR) | DFID (FTEs)
NB: Year 1: Dec 2014-August 2015; Year 2: Sep 2015-Aug 2016; Year 3: Sep 2016-Aug.2017; Year 4: Sep. 2017-Aug 2018; Year 5: Sep. 2018-Aug 2019; Year 6: Sep. 2019-Aug 2020.
* Revised indicators in July 2019
Updated on: 19 Feb 2020
Exchange rate: | 1GBP=NPR 145/-